## Sheet1
Defect ID | TC id | TS id | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Module/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Retail_User_UserRegistraion_TC001 | TS009 | Cycle1 |  | Integration Testing | Release1 | 07.09.2021 | Meghna | Mehfooza | 2 | Register User |  | Defect:Drop down list does not contain all the states corresponding to the country.Steps to reproduce:All the states corresponding to the country choosen shoul be displayed in list | QA |  |  | U I | Y | Defect | 1-Critical |  | Not able to find the state under the choosen country
2 | Retail_User_UserRegistraion_TC005 | TS059 | Cycle2 |  | System Testing | Release2 | 07.09.2021 | Meghna | Mehfooza | 2 | Register User |  | Defect:Telephone numbers which has more 10 characters are accepted.Steps to reproduce:Number of characters for telephone numbers should be set as equal to 10.Expectation:Error message should be displayed if number of characters is more than 10 | QA |  | 1 | Coding Error | Y | Defect | 1-Critical |  | Invalid telephone numbers having more than 10 charcters are accepted without any proper validation
3 | Retail_User_UserRegistraion_TC015 | TS121 | Cycle2 |  | System Testing | Release2 | 07.09.2021 | Meghna | Mehfooza | 2 | Register User |  | Defect:Default selection for the radio button is "No".Steps to reproduce: By default non of the values in radio button has to be selected.Expectation:In registration page New letter Subscription should not be kept as selected by default | QA |  | 2 | Coding Error | Y | Defect | 2-High |  | Subscripttion for news letter is already choosen as no
4 | Retail_User_UserRegistr ation_TC008 | TS015 | Cycle2 |  | System Testing | Release2 | 07.09.2021 | Meghna | Mehfooza | 2 | Register User |  | Defect:email without "@" symbol is accepted by the Web Page.Expectations:email has to be verified by checking whether "@" is present or not | QA |  | 2 | Coding Error | Y | Defect | 3-Medium |  | Email id without "@" symbol is taken into consideration
5 | Retail_User_UserRegistration_TC009 | TS029 | Cycle2 |  | System Testing | Release2 | 07.09.2021 | Meghna | Mehfooza | 2 | Register User |  | Defect:Email which is not verified is being accepted by the web page.Expectation:Only verified email has to be accepted by the web page | QA |  |  | Coding Error | Y | Defect | 3-Medium |  | Email id which is not verified is taken into web page