## User
Test Cases and Execution status tracking
Task :Creation of Test Cases
Project | Retail Shop
Sl no. | Module | # of Test Cases written and Reviewed | Date | Estimated effort | Actual Effort | Reason for variannce if any
1 | User->My Account | 32 | 6.09.2021 | 120 | 120 | N/A
2 | User->My Order | 5 | 6.09.2021 | 60 | 60 | N/A
3 | Admin->Order | 11 | 6.09.2021 | 120 | 120 | Requirement clarity was not mentionned
4 | Admin->Returns | 32 | 6.09.2021 | 60 | 60 | N/A
| Total # of test cases | 80